## Programs
ID | Name | Description | Start Date | End Date | Status | Created At
prog-1 | Spacecraft Design Project | Complete spacecraft design and development program | 2024-01-01 | 2024-12-31 | active | 2025-09-24 15:41

## Work Packages
ID | Program ID | Name | Description | Parent ID | Order | Created At
wp-1 | prog-1 | Thermal Subsystem | Thermal management and analysis |  | 1 | 2025-09-24 15:41
wp-2 | prog-1 | Electrical Subsystem | Power distribution and control systems |  | 2 | 2025-09-24 15:41
wp-3 | prog-1 | Software Subsystem | Flight control and communication software |  | 3 | 2025-09-24 15:41

## Tasks
ID | Work Package ID | Title | Description | Status | Task Type | Assigned Resource | Assigned Person ID | Progress | Estimated Days | Remaining Days | Current Workflow Step | Completed Workflow Steps | Dependencies | Due Date | Priority | Tags | Created At | Updated At
task-1 | wp-1 | Thermal Analysis Simulation | Perform comprehensive thermal analysis simulation | todo | parts_assembly | mechanical_engineer | person-1 | 0 | 5 | 5 | design |  |  | 2024-11-25 | medium | thermal, simulation | 2025-09-24 15:41 | 2025-09-24 15:41
task-2 | wp-2 | Power Distribution Unit Design | Design power distribution unit for spacecraft | todo | parts_assembly | electrical_engineer | person-2 | 15 | 8 | 7 | design |  |  | 2024-11-28 | high | electrical, power | 2025-09-24 15:41 | 2025-09-24 15:41
task-3 | wp-3 | Flight Control Software Module | Implement flight control software module | in_progress | software | software_engineer | person-3 | 65 | 10 | 2 | testing | design, implementation |  | 2024-11-20 | high | software, control | 2025-09-24 15:41 | 2025-09-24 15:41
task-4 | wp-1 | Structural Load Testing | Perform structural load testing procedures | in_progress | testing | production | person-4 | 40 | 3 | 2 | procedure | setup |  | 2024-11-22 | medium | testing, structural | 2025-09-24 15:41 | 2025-09-24 15:41
task-5 | wp-3 | Communication Protocol Implementation | Implement spacecraft communication protocols | in_progress | software | software_engineer | person-3 | 80 | 6 | 1 | code_review | design, implementation, testing |  | 2024-11-21 | high | software, communication | 2025-09-24 15:41 | 2025-09-24 15:41
task-6 | wp-2 | Antenna Design Specifications | Create detailed antenna design specifications | review | parts_assembly | system_lead | person-5 | 95 | 4 | 0 | review_approval | design, hardware, testing |  | 2024-11-19 | medium | antenna, rf | 2025-09-24 15:41 | 2025-09-24 15:41
task-7 | wp-2 | Battery Management System | Design and implement battery management system | review | parts_assembly | electrical_engineer | person-2 | 90 | 7 | 1 | review_approval | design, hardware, testing |  | 2024-11-23 | high | battery, power | 2025-09-24 15:41 | 2025-09-24 15:41
task-8 | wp-1 | Initial Requirements Analysis | Complete initial requirements analysis for thermal system | completed | documentation | system_lead | person-5 | 100 | 3 | 0 | release | draft, review, approval |  | 2024-11-10 | high | requirements, documentation | 2025-09-24 15:41 | 2025-09-24 15:41
task-9 | wp-1 | Preliminary Design Review | Conduct preliminary design review for thermal subsystem | completed | milestone | system_lead | person-5 | 100 | 2 | 0 | completion | planning, execution, review |  | 2024-11-08 | high | milestone, review | 2025-09-24 15:41 | 2025-09-24 15:41
task-10 | wp-1 | Environmental Testing Setup | Set up environmental testing equipment and procedures | blocked | testing | production | person-4 | 25 | 5 | 7 | hardware | setup |  | 2024-11-18 | critical | testing, environmental | 2025-09-24 15:41 | 2025-09-24 15:41

## Persons
ID | Name | Resource Type | Email | Initials | Is Active | Created At
person-1 | John Smith | mechanical_engineer | john.smith@aerospace.com | JS | TRUE | 2025-09-24 15:41
person-2 | Sarah Chen | electrical_engineer | sarah.chen@aerospace.com | SC | TRUE | 2025-09-24 15:41
person-3 | Alex Rodriguez | software_engineer | alex.rodriguez@aerospace.com | AR | TRUE | 2025-09-24 15:41
person-4 | Emily Johnson | production | emily.johnson@aerospace.com | EJ | TRUE | 2025-09-24 15:41
person-5 | Michael Davis | system_lead | michael.davis@aerospace.com | MD | TRUE | 2025-09-24 15:41

## Sprints
ID | Program ID | Name | Start Date | End Date | Status | Task IDs | Created At
sprint-1 | prog-1 | Sprint 3 | 2024-11-15 | 2024-11-29 | active | task-1, task-2, task-3, task-4, task-5, task-6, task-7, task-8, task-9, task-10 | 2025-09-24 15:41

## Comments
ID | Task ID | Author | Content | Created At
comment-1 | task-3 | John Smith | Testing is progressing well. Found minor issue with attitude control precision that needs addressing. | 2025-09-24 13:41
comment-2 | task-3 | Maria Brown | Implementation phase completed ahead of schedule. Moving to testing phase. | 2025-09-23 15:41

## Time Entries
ID | Task ID | User | Start Time | End Time | Duration (minutes) | Description | Is Active | Created At